## Slide 1: Lite Book Reader
Group 26: Mario Jose George Garcia, Thomas Seaman, Ian Nkwocha, Berk Demir, Zaki Kalha, Buluthan Bozkurt

## Slide 2: ABOUT OUR TEAM
Team Leader: Mario (Spanish, English and Arabic)
Team Admin: Thomas (English)
Git Master: Ian (English)
Team Member: Berk (Turkish, German, English,…)
Team Member: Buluthan (Turkish, English)
Team Member: Zaki (Arabic, English)

## Slide 3: PROPOSED APPROACH - PLATFORMS
HTML/CSS
Back-end(Liquibase, PostgresSQL)
NodeJS Server

## Slide 4: PROPOSED TIMELINE
October-December Cycle
Finish gathering requirements and creating specifications (11th of November)
Learn more about NodeJS as a team and begin working on creating server (25th of November)
Working back-end able to send requests to API and process results (13th of December)
Start creating HTML and CSS Interface (13th of December)
January-March Cycle
Start implementing connection of front & back-end (30th of January)
Working Server (24th of February)
Have a built GUI (9th of March)
March-May Cycle
Fully functional application(front-end, back-end and server (13th of April)

## Slide 5: PROPOSED APPROACH - MANAGEMENT
Split team to work in 2 back-end teams and a front-end team
Two-week sprint cycles
Meetings three times a week
  Source new requirements
  Making adjustments/ additions to Kanban Board
Kanban Board
  Dividing up and tracking tasks
  Paired Programming to reduce skill deficiencies
GitLab
  Version control and backups
  Automatic integration testing
University email and calendar
  Planning meetings & liaison

## Slide 6: WHY WE ARE SUITABLE
Technical skills:
  REST API, ASP.NET Web API 2, C#, MongoDB, UI design
  Big Data
  HTML, CSS, Javascript, Ajax
  JQuery, JQuery Mobile
  Databases (SQL)
Workplace experience:
  Extensive experience with REST API
  Agile techniques to plan and create a website for a company
  Team-leader has experience working abroad as a team leader in different companies.

## Slide 7: SUMMARY – KEY POINTS
Teams Structure (1 Front-End, 2 Back-End)
Kanban Board And Scrum Cycles
Experience With Rest API Will Help